## Sheet1
Sprint #2 Backlog
Team 60 :: Hungry@CMU
Product Owner: Karthik Murugan
Feature | Actor(s) | Estimate (hrs) | Developer | Additional Notes
Create new restaurant | Admin | 1 | Luke | Restaurants may only be created by admins. This includes optionally uploading a "main" photo with all other relevant restaurant model data.
Edit existing restaurant | Admin, Employee | 1.5 | Luke | Once created, restaurant information may be edited by admins. In addition, restaurant managers *should* have ability to edit their managed restaurant's information.
Grant registration privilege to new restaurant employee | Admin, Employee | 2 | Luke | Restaurant employees cannot register before having received a unique registration generated by an admin. The link directets them to page with necessary form to complete.
Deactivate any other user | Admin | 0.5 | Luke | An admin should be able to deactivate any other type of user (students & restaurant employees).
Create new administrator | Admin | 1 | Luke | An admin should be able to create a new administrator.
View account page | Student | 1 | Luke | Once authenticated, students should have ability to visit some 'account summary' page.
Place single order (one or more food items) | Student | 3 | Karthik | A student should be able to create an order by adding food items (from single restaurant) to an order. After submitting the order, she should receive an email (similar to a receipt) with order details. When the order is complete, she should receive a second email notification. She should not be able to place an order if she already has a pending order in the system.
View order history | Student | 1.5 |  | In addition to viewing expected information on 'account summary' page, students should be able to browse/view past orders. At this stage, a student should be able to seamlessly reorder identical orders.
Edit account information (where applicable) | Student
Create new food items (belong to a restaurant's menu) | Employee | 2 | Karthik | An employee should be able to create new food items for her restaurant's menu. When successfully saved to the system, restaurants' items are displayed in some logical manner (depicting a menu) where students view the restaurant's details.
Edit restaurant food items | Employee | 1 | Karthik
Browse restaurant food items | Student |  | Karthik
Implement operating hours (custom model field) | n/a |  |  | Find effective way to storing and later displaying restaurants' operating hours.
Search/filter restaurants by operating hours ( a ) | Student |  | Karthik
Search/filter restaurants by cuisine ( b ) | Student |  | Karthik
Browse only restaurants with vegetarian options ( c ) | Student |  | Karthik
Search/filter restaurants with any combination of (a, b, c) | Student |  | Karthik
Restaurant Employee Fixtures | n/a | 0.5
Administrator Fixtures | n/a | 0.5
Food Item Fixtures | n/a | 0.5
Order Fixtures | n/a | 0.5